## DTGen
		Estimated
Release	Weeks	Delivery Date	Description		Week Ending:					Week Ending:					Week Ending:
Current AsOf:		13-Jul-2012			Jul 20	Jul 27	Aug 03	Aug 10	Aug 17	Aug 24	Aug 31	Sep 07	Sep 14	Sep 21	Sep 28	Oct 05	Oct 12	Oct 19	Oct 26	Nov 02	Nov 09	Nov 16	Nov 23	Nov 30	Dec 07	Dec 14	Dec 21	Dec 28	Jan 04	Jan 11
0.12	3	03-Aug-2012	Minor/Simple Defects Repair		X	X	X
0.13	5	07-Sep-2012	QA1: Unit Testing					X	X	X	X	X
0.14	4	05-Oct-2012	QA2: Integration Testing and Critical Fixes					X	X	X	X
0.15	3	26-Oct-2012	Added Datatypes					X	X	X
0.16	3	16-Nov-2012	High Priority Fixes					X	X	X
0.17	4	14-Dec-2012	Capacity Increases					X	X	X	X
0.18	4	11-Jan-2013	Low Priority Fixes					X	X	X	X
1	3	01-Feb-2013	Cleanup and Documentation
1.1	3	22-Feb-2013	Developer Friendly Enhancements
1.2	5	29-Mar-2013	Performance Test Data Generation